## Sprint Backlog
Story	Sprint backlog item	Task	Volunteer	Task details	Initial effort estimate (hrs)	New estimates of effort remaining at end of					Status
				Day 1	Day 2	Day 3	Day 4	Day 5	Day 6
US001	To allow only bank employee to be able to login to bank web site	Task 1	Renuka	Create all relevant tables	2					Closed
		Task 2	Renuka	Creating test data	2					Closed
		Task 3	Renuka	Create all pojo classes	2					Closed
		Task 4	Kratika	Create db connection	1					Closed
		Task 5	Siddhanta	Create styling body for login page	2					Closed
		Task 6	Kratika	Html form creation	1					Closed
		Task 7	Kratika	Form validation	1					Closed
		Task 8	Renuka	Implementing service class	1	0.5					Closed
		Task 9	Kratika	Dao class	1	0.5					Closed
		Task 10	Siddhanta	Header and footer page	3					Closed
		Task 11	Siddhanta	Creating home page for cashier and executive pages	2					Closed
		Task12	Palak	Creating test data	2					Closed
		Task 13	Kratika	Login servlet creation	2					Closed
		Task 14	Renuka	Testing and review	3	3	3	3				Open
US002	To allow customer-account executive to create new customer	Task 1	Siddhanta	Add header and footer	0.5	0.5	0.5					Closed
		Task 2	Palak	Styling body	2					Closed
		Task 3	Palak	Creating form	2					Closed
		Task 4	Abhishek	Validating form	2					Closed
		Task 5	Abhishek	Servlet creation	2					Closed
		Task 6	Abhishek	Implementing service class	1					Closed
		Task 7	Palak	Writing dao class	2					Closed
		Task 8	Abhishek	Integration	2	2	2	2	2			Closed
		Task 9	Kratika	Testing and revew	2	2					Closed
		Task 10	Kratika	Refactoring	1	1					Closed
US003	To allow customer-account executive to update existing customer information	Task 1	Kratika	Add header and footer	0.5	0.5					Closed
		Task 2	Siddhata+Palak	Styling body	2,2	2+2					Closed
		Task 3	Ahmmedali	Creating form and validate	3	1	1					Closed
		Task 4	Ahmmedali	Servlet creation	2					Closed
		Task 5	Ahmmedali	Writing dao class	2					Closed
		Task 6	Ahmmedali	Creating show page with details	3	3					Closed
		Task 7	Ahmmedali	Validate form	1	1					Closed
		Task 8	Ahmmedali	Implement servlet	1	1					Closed
		Task 9	Ahmmedali	Implementing service class	1	1					Closed
		Task 10	Ahmmedali	Implementing dao class	2	2	2					Closed
		Task 11	Kratika	Integration	2	2	2	2	2			Closed
		Task12	Kratika	Review and testing	2	2	2	2	2			Closed
		Task 13	Ahmmedali	Refactoring	1	1	1	1				Open
US004	To allow customer-account executive to delete existing customer	Task 1	Kratika	Creating form	1	1					Closed
		Task 2	Siddhanta	Apply styling	2	2					Closed
		Task 3	Sujith	Apply validations	2					Closed
		Task 4	Sujith	Include header and footer	0.5	0.5					Closed
		Task 5	Sujith	View account details	2	2					Closed
		Task 6	Sujith	Pull out account details from customer search form	1	1					Closed
		Task 7	Sujith	Servlet creation	2					Closed
		Task 8	Sujith	Implementing dao class	3					Closed
		Task 9	Sujith	Update customer as inactive in db	1	1					Closed
		Task 10	Sujith	Redirection to success or error page	0.5	0.5					Closed
		Task 11	Sujith	Integration	2	2					Open
		Task12	Sujith	Review and testing	2	2					Open
		Task 13	Sujith	Refactoring	1	1					Open
US005	To allow customer-account executive to view customer status for all customers	Task 1	Siddhanta	Add header and footer	0.5	0.5					Closed
		Task 2	Siddhanta	Styling body for status page	2	2					Closed
		Task 3	Abhishek	Servlet creation	2	2					Closed
		Task 4	Palak	Implementing service class	2	2	2					Closed
		Task 5	Palak	Dao class	2	2	2					Closed
		Task 6	Abhishek	Styling body for details page	2	2	2					Closed
		Task 7	Palak	Writing queries	1	1	1					Closed
		Task 8	Abhishek	Display page of customer profile	4	4					Closed
		Task 9	Akshay	Integration	2	2	2	2				Closed
		Task 10	Akshay	Review and testing	2	2	2	2				Closed
		Task 11	Kratika	Refactoring	1	1	1	1	1			Closed
US006	To allow customer-account executive to create new account for existing customer	Task 1	Akshay	Add header and footer	0.5	0.5					Closed
		Task 2	Akshay	Creating form	1					Closed
		Task 3	Akshay	Styling body and validations	2					Closed
		Task 4	Akshay	Servlet creation, connecting to db	4	4					Closed
		Task 5	Akshay	Creating search method in dao to verify ssn id	2	1					Closed
		Task 6	Akshay	Create insert method	2		2					Closed
		Task 7	Akshay	Display id in webpage	0.5	0.5					Closed
		Task 8	Akshay	Integration	2	2	2					Closed
		Task 9	Akshay	Review and testing	2	2	2					Closed
		Task 10	Akshay	Refactoring	1	1	1					Closed
US007	To allow customer-account executive to delete existing account.	Task 1	Kratika	Add header and footer	0.5	0.5					Closed
		Task 2	Kratika	Creating form	2	2					Closed
		Task 3	Siddhanta	Styling body	1	1	1					Closed
		Task 4	Sujith	Validate form	0.5	0.5	0.5	0.5				In Progress
		Task 5	Sujith	Servlet and dao creation	3	3	3	3				In Progress
		Task 6	Sujith	Display account details	3	3	3	3				In Progress
		Task 7	Sujith	Displaying balance	1	1	1	1				In Progress
		Task 8	Sujith	Servlet and dao creation	3	3	3	3				In Progress
		Task 9	Sujith	Integration	2	2	2	2				Open
		Task 10	Sujith	Review and testing	2	2	2	2				Open
		Task 11	Sujith	Refactoring	1	1	1	1				Open
US008	To allow customer-account executive to view account status for all accounts	Task 1	Abhishek	Creating method for gettng account status	1	1	1	1				Closed
		Task 2	Abhishek	Creating servlet and calling method from dao	2	2	2					Closed
		Task 3	Abhishek	Displaying details in webpage	4	2	2					Closed
		Task 4	Kratika	Add header and footer and styling	1	1	1					Closed
		Task 5	Kratika	Integration	2	2	2	2	2	2		Closed
		Task 6	Kratika	Review and testing	2	2	2	2	2	2		Closed
		Task 7	Kratika	Refactoring	1	1	1	1	1	1		Closed
US009	To allow customer-account executive to pull information of a customer	Task 1	Siddhanta	Add header and footer	2	2	2					Closed
		Task 2	Kratika	Creating form	0.5	0.5	0.5					Closed
		Task 3	Siddhanta	Styling body	0.5	0.5	0.5					Closed
		Task 4	Ahmmedali	Validate form	1	1	1					Closed
		Task 5	Ahmmedali	Servlet creation	1	1	1					Closed
		Task 6	Ahmmedali	Dao class	3	3	3	3				Closed
		Task 7	Ahmmedali	Show result	1	1	1	1				Closed
		Task 8	Ahmmedali	Integration	2	2	2	2	2			Closed
		Task 9	Ahmmedali	Review and testing	2	2	2	2	2			Closed
		Task 10	Ahmmedali	Refactoring	1	1	1	1	1			Closed
US010	To allow cashier/ teller to pull information for a specific account of a customer	Task 1	Palak	Add header and footer	2	2	2					Closed
		Task 2	Kratika	Creating form	0.5	0.5	0.5					Closed
		Task 3	Siddhanta	Styling body	0.5	0.5	0.5					Closed
		Task 4	Akshay	Validate form	1	1	1	1				Closed
		Task 5	Akshay	Servlet creation	1	1	1	1				Closed
		Task 6	Akshay	Dao class	3	3	3	3	3			Closed
		Task 7	Akshay	Show result	1	1	1	1	1			Closed
		Task 8	Akshay	Integration	2	2	2	2	2	2		Closed
		Task 9	Akshay	Review and testing	2	2	2	2	2	2		Closed
		Task 10	Akshay	Refactoring	1	1	1	1	1	1		Closed
US011	To allow cashier/ teller to deposit money into customer account	Task 1	Palak	Add header and footer	2	2	2					Closed
		Task 2	Kratika	Creating form and validate	0.5	0.5	0.5					Closed
		Task 3	Siddhanta	Styling body	2	2	2	2	2			Closed
		Task 4	Renuka	Servlet creation	2	2	1	1				In Progress
		Task 5	Renuka	Dao class	2	2					Closed
		Task 6	Renuka	Service class	2	2					Closed
		Task 7	Renuka	Integration	2	2	2	2				Open
		Task 8	Renuka	Review and testing	2	2	2	2				Open
		Task 9	Renuka	Refactoring	1	1	1	1				Open
US012	To allow cashier/ teller to withdraw money from customer account	Task 1	Siddhanta	Add header and footer	2	2	2	2				Closed
		Task 2	Kratika	Creating form	0.5	0.5	0.5					Closed
		Task 3	Siddhanta	Styling body	2	2	2	2				Closed
		Task 4	Renuka	Validate form	2	2	2					Closed
		Task 5	Renuka	Servlet creation	2	2	2	2				In Progress
		Task 6	Palak	Dao class	2	2					Closed
		Task 7	Palak	Service class	2	2					Closed
		Task 8	Renuka	Integration	2	2	2	2				Open
		Task 9	Renuka	Review and testing	2	2	2	2				Open
		Task 10	Palak	Refactoring	1	1	1	1				Open
US013	To allow cashier/ teller to transfer money from customer account	Task 1	Palak	Add header and footer	2	2	2	2				Closed
		Task 2	Kratika	Creating form and validate	0.5	0.5	0.5					Closed
		Task 3	Siddhanta	Styling body	2	2	2	2				Closed
		Task 4	Kratika	Perform account check	1	1	1					Closed
		Task 5	Abhishek	Create transaction page	2	2	2	2	2	2		Closed
		Task 6	Kratika	Perform validations	2	2	2					Closed
		Task 7	Kratika	Balance checking	1	1	1					Closed
		Task 8	Palak	Create dao class	2	2	2	2				Closed
		Task 9	Palak	Create servlet	2	2	2	2	2			Closed
		Task 10	Palak	Creatng service class	2	2	2	2	2			Closed
		Task 11	Ahmmedali	Integration	2	2	2	2	2	2		Closed
		Task12	Ahmmedali	Review and testing	2	2	2	2	2	2		Closed
		Task 13	Renuka	Refactoring	1	1	1	1				Open
US014	To allow cashier/ teller to pull account statement for a customer-account	Task 1	Kratika	Add header and footer	1	1	1	1	1			Closed
		Task 2	Kratika	Creating form and validate	0.5	0.5	0.5	0.5	0.5			Closed
		Task 3	Siddhanta	Styling body	1	1	1	1				Closed
		Task 4	Abhishek	Implementing service and servlet class	1.5	1.5	1.5	1.5	1.5	1.5		Closed
		Task 5	Abhishek	Database operations	3	3	3	3				Closed
		Task 6	Abhishek	Creating view page with printing facility	4	4	4	4	4			Closed
		Task 7	Siddhanta	Integration	4	4	4	4	4			Closed
		Task 8	Siddhanta	Review and testing	2	2	2	2	2	2		Closed
		Task 9	Siddhanta	Refactoring	1	1	1	1	1	1		Closed
TOTAL:					256	199	151.5	110.5

				13

## Sprint 1 Burndown Chart
				Sprint Timeline / Remaining Effort (hrs)

Day0	Day1	Day2	Day3	Day4	Day5	Day6
252	198	154	120

252	210	168	126	84	42	0